## WBS Tree Diagram - EPM
WORK BREAKDOWN STRUCTURE
PROJECT TITLE | EPM Automated Property Ledger | COMPANY NAME | Excel Property Management
PROJECT MANAGER | Hillary Adams | DATE | 2023-10-31
EPM Property Ledger Automation
1 Project Planning
1.1 Define project scope
1.2 Identify requirements
1.3 Plan project timeline
1.1.1 Project Plan Scope
1.2.1 Requirements Document
1.3.1 Risk management plan and milestones
2 Design
2.1 Design document
2.2 UI design
2.3 Security design
2.1.1 Design system architecture and database schema
2.3.1 Authentication and authorization
3 Development
3.1 Develop UI
3.2 Develop Excel VBA system
3.3 Develop web implementation
3.1.1 Develop menu-based UI
3.1.2 Develop UI legacy mode prompt
3.1.3 Develop business analyst UI
3.2.1 Develop database to schema specification
3.2.2 Develop user permission models
3.2.3 Develop system testing and QA procedures
3.3.1 Develop web interface
3.3.2 Develop database and server-side logic
3.3.3 Integrate Excel VBA components
3.3.4 Develop system documentation and user manuals
4 Deployment
4.1 Testing and validation
4.2 Integration deployment
4.3 Post-deployment plan
4.1.1 Conduct validation testing
4.1.2 Conduct user acceptance testing
4.1.3 Conduct load testing
4.2.1 Configure and deploy system to production server
4.2.2 Migrate data from existing system
4.3.1 Develop post-deployment and maintenance plan
5 Maintenance and Support
5.1 Address system bugs
5.2 Provide user training
5.3 System upgrades
5.1.1 Perform updates and patches
5.1.2 Monitor system performance and uptime
5.2.1 Maintain documentation
5.2.2 Provide technical support
5.3.1 Develop enhancement requests
5.3.2 Plan and implement new features and upgrades
5.4 System recovery
5.4.1 Communicate system changes to users
5.4.2 Develop a disaster recovery plan
5.4.3 Schedule regular system backups
5.4.4 Perform data recovery testing
2.2.1 Design VBA Excel UI
2.2.2 Design web-based UI